## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0014_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1963 |  |  | Transmital Date: 25 Mar 2023
Document Title: Data Sheets For Corrosion Coupon/ Probe |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1963 |  |  | Transmital Date: 25 Mar 2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0014_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-07367 | 2023-04-09 | ملاحظه گردید.
2 | نقطه نظرات ذينفع اصلي بر روي اين مدرك در نظر گرفته شود. |  | BK-SUR-ENG-INS-02-07367 | 2023-04-09 | رویت گردید.
3 | با توجه به P&ID ارائه شده، CP ها از نوع محلي تعريف شده است، در صورتي كه اين مدرك از نوع ترانسميتر در نظر گرفته شده است. تناقض بين مدارك بررسي و اصلاح گردد. |  | BK-SUR-ENG-INS-02-07367 | 2023-04-09 | نوت 11 اصلاح گردید.
4 | بنظر مي رسد كه نوت شماره 11- جنرال با CP ها همخواني ندارد. موارد بررسي و اصلاح گردد. |  | BK-SUR-ENG-INS-02-07367 | 2023-04-09
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 9 Apr 2023 |  |  |  |  | Date: