## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-T-1753 |  |  | Transmital Date: 02/01/2023
Document Title: Emission and Effluent Summary |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-T-1753 |  |  | Transmital Date: 02/01/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0007_D01 |  |  | CRS Status:C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ترکیب درصد و میزان گازهای ارسالی به اتمسفر ناشی از سوختن در مشعل، در دو حالت نرمال و اضطراری در مدرک درج گردد. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | مشخصات گاز حاصل از سوخت پس از دریافت از سازندگان به مدرک اضافه میگردد.
2 | میزان حداکثر دبی Contaminated Water بر اساس موارد مندرج در مدرک Drainage Philosophy در این مدرک درج گردد. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | اعمال گردید.
3 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021