## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0007_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2252 |  |  | Transmital Date: 18 Jul 2023
Document Title: PMR For F&G Devices |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-2252 |  |  | Transmital Date:18 Jul 2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0007_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | ملاحظه گردید.
2 | در خصوص كابل هاي F&G شفاف سازي گردد كه در محدوده شرح كار كدام وندور مي باشد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | شرح کار کابل های F&G در حوزه کاری پیمانکار می باشد که در مدرک CABLE LIST مشخص گردیده است.
3 | در خصوص ديتكتورهايي كه هم بصورت آدرس پذير و هم Convential در پروژه موجود مي باشند در جدول بصورت مجزا ذكر گردد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | با توجه به کامنت های پیشین ذينفع اصلی ارائه جزئیات در مدرک MR ضرورتی ندارد و با توجه پیوست مدرک دیتاشیت، وندور مربوطه باید به آن مراجع بکند.
6 | مقدار SIL ادوات مطابق با مدارك پروژه مشخص گردد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26
5 | 2 Years spare parts مطابق اسناد پيمان در نظر گرفته شود. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | در بخش 5.1.2 SPARE PARTS به وضوح بیان شده است.
6 | مدرك F&G Location Layout و F&G Device Datasheet براي ساختمان كنترل نهايي نمي باشد. در صورت هر گونه تغيير در اين مدرك نيز بايد منعكس گردد. نهايي شدن شدن اين مدرك منوط به نهايي شدن مدارك پيش نياز مي باشد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | ملاحظه گردید.
7 | با توجه به كامنت هاي درج شده در بالا، اين مدرك به ذينفع اصلي ارسال نشده است، لذا اين ترانسميتال با همين رويژن جايگزين گردد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | اعمال گردید.
1 | لزوم ارائه مدارك ITP/QCP توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | اعمال گردید.
2 | جهت يكسان سازي در كليه متون، كلمهVendor جايگزين Supplier گردد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | اعمال گردید.
3 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | مدرک اصلاح گردید.
The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENTor EPC/EPD (GC) CONTRACTOR before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification.
4 | لغت ''Purchaser" مي بايست در قسمت General Definition تعريف گردد. |  |  | 2023-07-26 | مدرک اصلاح گردید.
5 | آيتم هاي ذيل از جدول Attachment 2 حذف گردد: |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | مطابق نظر کارفرمای محترم اصلاح گردید.
Non-Destructive Testing/Examination Procedures
Hardness Test Reports
Non-Conformities Report
Pressure Test Reports / Certificates
6 | از رديف 20 جدول Attachment 2 عبارت (5.1.3) حذف گردد. |  | BK-SUR-ENG-INS-02-08185 | 2023-07-26 | مطابق نظر کارفرمای محترم اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 26 Jul 2023 |  |  |  |  | Date: