## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-EL-MR-0013_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1639 |  |  | Transmital Date: 29-Nov-2022
Document Title: PMR For Transmission Over head Line - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0109-EL-TR-1639 |  |  | Transmital Date: 29-Nov-2022
[5 empty] | CRS No: PEDCO-CRS-BK-BK14-PEDCO-110-EL-MR-0013_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | No Comment. Note: -"Earthing Layout For Electrical Tower (Gantry) of Well Pads" document shall be added to reference document and attached to MR. -In case of any changes in prerequisite documents such as Plan&Profile that lead to the transmission line length, this document shall be revised. |  | BK-SUR-ENG-ELE-01-06374 | 2022-12-10 | اعمال خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 10-Dec-22 |  |  |  |  | Date: