## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-EL-MT-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1633 |  |  | Transmital Date: 28-Nov-2022
Document Title: MTO For Transmission Over Head Line - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-1633 |  |  | Transmital Date: 28-Nov-2022
[5 empty] | CRS No: PEDCO-CRS-BK-BK14-PEDCO-110-EL-MT-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | There is confilict between this document and Over Head Line Plan and Profile-BK14 form point of No. of towers view, it shall be rechecked and modified. |  | BK-SUR-ENG-ELE-01-05771 | 2022-09-28 | اصلاحات لازم در مقادير بر اساس نقشه پلان پروفيل تجديدنظر 02 با كد BK-BK14-PEDCO-110-EL-DW-0001-D02 انجام گرديد. |  |  | Noted and Closed.
2 | This document shall be revised after finalizing or minnor commets on Over Head Line Plan and Profile-BK14. |  | BK-SUR-ENG-ELE-01-05771 | 2022-09-28 | ملاحظه گرديد. |  |  | Noted and Closed.
3 | MTO for Gantry in T-off for BK14/Goreh/Binak and Gantry in well No. BK14 will be checked after submitting and finailizing or minnor comments on "Installation Detail & Notes for Connection OHL to Gantries for Wells". |  | BK-SUR-ENG-ELE-01-06373 | 2022-12-10 | مدرک مورد نظر با شماره ترنسمیتال 1844 برای آن کارفرمای محترم ارسال شده است که مورد تأیید است. همچنین مدرک Oveall Single Line Diagram نیز نهایی شده است که تمامی نقطه نظرات کارفرما منظور گردیده است. لذا این مدرک قابل تولید می باشد.
4 | Earthing material take off for gantry in T-off for BK14/Goreh/Binak and gantry in well No. BK14, shall be added to attchment#02. (Gnatry earthing layout shall be shown in "Earthing Layout For Electrical Tower (Gantry) of Well Pads" base on comments on TR-1609 to checking earthing MTO for gantries) |  | BK-SUR-ENG-ELE-01-06373 | 2022-12-10 | در ردیف 14 تا 17 از پیوست دوم، لیست تجهیزات سیستم ارتینگ اضافه گردید.
5 | Base on consultant response to NISSOC comment about earthing of tower, earthing layout for tower (TR-1609) shall be modified to checking tower earthing MTO in attchment#01. |  | BK-SUR-ENG-ELE-01-06373 | 2022-12-10 | اعمال خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 10-Dec-22 |  |  |  |  | Date: