## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0004_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1220 |  |  | Transmital Date: 30 Jul 2022
Document Title: Instrument/F&G Cable Trench/Route Layout Drawing |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1220 |  |  | Transmital Date: 30 Jul 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0004_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-15 | ملاحظه گردید
2 | با توجه به اينكه، مدارك مرتبط با اين مدرك هنوز تاييد و نهايي نشده است در صورت هر گونه تغيير در مدارك مرتبط موارد در اين مدرك نيز منعكس شود. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-15 | ملاحظه گردید
3 | با توجه به اينكه هنوز PLOT PLAN پروژه تائيد نشده است لذا اين مدرك بايستي پس از نهايي شدن PLOT PLAN نهايي گردد. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-15 | با توجه به آخرین مدرک PLOT PLAN بروز رسانی گردید
4 | بازگشت به كامنت يك مدرك پيشين، انعكاس آن در مدرك واضح نبوده لطفا شفاف سازي گردد. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-15 | مدرک اصلاح گردید
5 | بازگشت به كامنت شماره 2 مدرك پيشين ارتباطات بين اتاق كنترل قديم و جديد بصورت واضح مشخص و در قالب يك نوت نمايش داده شود. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-15 | با توجه به اینکه ساختمان کنترل جدید حذف شدههمه سیگنالها به ساختمان کنترل قدیم ارسال می شوند و مسیر کابل کشی بروز شده است
6 | در صورتي كه cross با بستر كابل هاي موجود (ابزاردقيق، برق) داشته باشيم، تاييد نماييد كه فاصله ايمن بر اساس مدارك پروژه و IPS در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-05462 | 2022-08-15 | با توجه به استاندارد IPS در صورت CROSS با کابل های موجود فاصله لازم رعایت می شود
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 15 Aug 2022 |  |  |  |  | Date: