## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2092 |  |  | Transmital Date: 5/13/2023
Document Title: Process Data Sheets For Inlet Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2092 |  |  | Transmital Date: 5/13/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظری مطرح نمی باشد. شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای مالی-قراردادی پیمانکار، مسئولیت بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار است. |  | 'BK-SUR-ENG-PCS-02-07720 | 2023-05-28 | مدرک بر اساس نقطه نظرات مطرح شده برروی مدرک DRUM سایزینگ و تغییر سایز نازل ورودی، بهروز رسانی شده و با توجه به اینکه مدرک پیشتر تایید شده ب مجددا با STATUS AFC ارسال میگردد.
2 | براساس بند 4.2.11 از مدرک Design Criteria، مقادیر Pv2 برای نازل ورودی باید کمتر از 3750 باشد که با سایز 8 اینچ برای نازل ورودی مغایر است. |  | 'BK-SUR-ENG-PCS-02-07720 | 2023-05-28 | مدرک بر اساس نقطه نظرات مطرح شده برروی مدرک DRUM سایزینگ و تغییر سایز نازل ورودی، بهروز رسانی شده و با توجه به اینکه مدرک پیشتر تایید شده ب مجددا با STATUS AFC ارسال میگردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: