## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-EL-MR-0011_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1983 |  |  | Transmital Date: 29/Mar/2023
Document Title:PMR FOR CAPACITOR BANK |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-1983 |  |  | Transmital Date: 29/Mar/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-EL-MR-0011_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
QC. Comments.
1 | در بند 6 (INSPECTION AND TESTS) عبارت "QC Plan" و "Quality Control Plan" به "Inspection and Test Plan (ITP)" تغيير يابد. |  | BK-SUR-ENG-ELE-02-07336 | 2023-04-05 | اعمال گردید.
2 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-ELE-02-07336 | 2023-04-05 | مدارک ذکر شده، همگی جز پیوست های قرارداد می باشد که به هنگام عقد قراداد با برنده مناقصه، منظور خواهد شد. لذا جهت یکپارچگی بین تمامی MR ها از آوردن آنها صرف نظر شده است.
3 | در بند 5.1.2 (SPARE PARTS) ، در دو سطر شماره مدرك Project spare part supply procedure ميبايست به E&C-QC-SP-1 تغيير يابد |  | BK-SUR-ENG-ELE-02-07336 | 2023-04-05 | اعمال گردید.
4 | در بند 11 (PRICE BREAKDOWN) ، در ايتمهاي شماره 2و3 شماره مدرك Project spare part supply procedure ميبايست به E&C-QC-SP-1 تغيير يابد |  | BK-SUR-ENG-ELE-02-07336 | 2023-04-05 | اعمال گردید.
5 | كلمات VENDOR و SUPPLIER در مدرك يكسان سازي شده و مطابق توضيحات بخش GENERAL DEFINITION از كلمه VENDOR استفاده گردد . |  | BK-SUR-ENG-ELE-02-07336 | 2023-04-05 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature | M.Fakharian
Date:04/04/2023