## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0009_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1606 |  |  | Transmital Date: 26 Nov 2022
Document Title: Instrument /F&G Cable List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1606 |  |  | Transmital Date: 26 Nov 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0009_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-06386 | 2022-12-10 | نظر کارفرمای محترم ملاحظه می گردد
2 | مدارك پيش نياز اين مدرك مانند I/O List داراي كامنت اساسي مي باشد. در صورت تغيير در هر كدام از مدارك، تغييرات در اين مدرك در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-06386 | 2022-12-10 | مدرک با آخرین نسخه P&ID , I/O LIST ( ESD . F&G , DCS ) بروز رسانی گردید
3 | شماره كابل ارائه شده در مدرك Cable schedule و Termination Diagram با هم تفاوت دارد. همسان سازي بين مدارك صورت پذيرد. MC-P-2302A در مدرك schedule |  | BK-SUR-ENG-INS-01-06386 | 2022-12-10 | اصلاح گردید
4 | ارتباط بين JBU-A-2103 و UCP در مدرك schedule مشخص شود. |  | BK-SUR-ENG-INS-01-06386 | 2022-12-10 | اصلاح گردید
5 | براي HN-9001، BR/BY/BB-9001 شماره كابل از فيلد به جعبه تقسيم در مدرك schedule اصلاح شود. |  | BK-SUR-ENG-INS-01-06386 | 2022-12-10 | کابل بین تجهیزات ( HN, BB , BR , BY ) و JB بر عهده وندور می باشد. کابل بین JB تا اتاق کنترل برعهده پیمانکار می باشد
6 | ارتباط بين LCP-MC-PK-2207 و سيستم DCS در مدرك schedule نظر گرفته شود. |  | BK-SUR-ENG-INS-01-06386 | 2022-12-10 | اصلاح گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 10 Dec 2022 |  |  |  |  | Date: