## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0014_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1396 |  |  | Transmital Date: 13/Sep/2022
Document Title: Mechanical Data Sheets For Slug Catcher |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ME-TR-1396 |  |  | Transmital Date: 13/Sep/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0014-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Design Pressure: F.V. / 9 |  | BK-SUR-ENG-MEC-01-05928 | 2022-10-19 | از آنجایی آیتم internal vaccum به صورت جداگانه در جدول وجود دارد، فشار F.V به صورت جداگانه اشاره شده است.
2 | برای نازل های بالای 2" می بایست reinforcing pad در نظر گرفته شود. |  | BK-SUR-ENG-MEC-01-05928 | 2022-10-19 | از آنجایی که طراحی reinforcement pad بر عهده وندور است، جزییات اشاره نشده است. مطابق نظر کارفرما به صورت * در جدول اعمال شد.
3 | سطوح فرآیندی با اطلاعات جدول Mechanical Design Data و مدرک P&ID تناقض دارد. |  | BK-SUR-ENG-MEC-01-05928 | 2022-10-19 | لطفا با ریویژن آخر مدرک P&ID چک شود. اطلاعات جدول اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: 10/19/2022 |  |  |  |  | Date: 09/03/2023