## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0016_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1315 |  |  | Transmital Date: 8/27/2022
Document Title: PMR For Level Gauge |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1315 |  |  | Transmital Date: 8/27/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0016_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | چرا جدول تجهیزات بجای ذکر در قسمت subject of the supply در general ذکر شده است. |  | 1401/2294/216495 | 19/06/1401 | اعمال گردید.
2 | تعداد و توضیحات تجهیزات با توجه به دیتاشیت نهایی بروز رسانی گردد. |  | 1401/2294/216495 | 19/06/1401 | اعمال گردید.
3 | صفحه 10 قسمت 11، عبارت other fee(if any) حذف گردد. |  | 1401/2294/216495 | 19/06/1401 | اعمال گردید.
4 | عبارت if require و if any از مدرک حذف گردد. |  | 1401/2294/216495 | 19/06/1401 | اعمال گردید.
5 | لیست مدارک پیوست اصلاح گردید.(دیتا شیت مرتبط نمی باشد) |  | 1401/2294/216495 | 19/06/1401 | اعمال گردید.
6 | آخرین ویرایش مدارک پیوست مد نظر قرار گیرد. |  | 1401/2294/216495 | 19/06/1401 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: