## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-PY-0008_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2061 |  |  | Transmital Date: 02-May-2023
Document Title: Electrical Equipment Arrangement Layout For Switchgear Building of Well Pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-2061 |  |  | Transmital Date: 02-May-2023
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0008_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک بر اساس نقشه معماری کلیدخانه بخش سیویل نامه شماره 20840 مورخ 1402-01-22 اصلاح گردد. |  | 1402-2294-86621 | 1402-03-07 | مطابق با هماهنگی های انجام شده بین بخش برق و سیویل این پیمانکار، کامنتهای نامه شماره 192776 و 86621 در مدرک سیویل اعمال گردید و مدرک با ترنسمیتال شماره 2337 برای آن کارفرمای محترم ارسال شده است. لازم به ذکر است مدرک معماری ملاک تولید این ویرایش قرار گرفته است. همچنین کامنتهای نامه شماره 20840 پیشتر در مدرکِ سیویل با ترنسمیتال 2231 مرتفع شده است.
2 | ارتباط کاندوییت بین اتاق باتری و ترانشه کلیدخانه تکمیل گردد. |  | 1402-2294-86621 | 1402-03-07 | با توجه به صحبتهای انجام شده با آقای سعادتیان، مقرر شد ارتباط بین فیوز باکسِ اتاق باتری و اسلیوهای ورودی به اتاق کلیدخانه از طریق سینی و لدر باشد. این امر در مدرک مسیرِ کابلِ کلیدخانه لحاظ خواهد شد. البته به صورت یک نوت در این مدرک عنوان می شود. همچنین نوت شماره 4 این موضوع را بیان می کند که ارتباط بین اتاق باتری و ترانشه از طریق کاندوییت خواهد بود.
| جهت استفاده بهتر از فضای اتاق باتری، Rack باتری شماره 13 90 درجه چرخانده شود. |  | 1402-2294-86621 | 1402-03-07 | مطابق با هماهنگی های انجام شده بین بخش برق و سیویل، کامنتهای نامه شماره 192776 و 86621 در مدرک سیویل اعمال گردید و مدرک با ترنسمیتال شماره 2337 برای آن کارفرمای محترم ارسال شده است. لازم به ذکر است مدرک معماری ملاک تولید این ویرایش قرار گرفته است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Gh.Saadatian | Signature |  |  |  | Clarified By: | Signature
| Date: 10-May-23 |  |  |  |  | Date: