## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-AR-DW-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2300 |  |  | Transmital Date:8/12/2023
Architectural Drawing For CCTV Control Room- Binak GCS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-T-2300 |  |  | Transmital Date: 8/12/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0008_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک پلات پلان به فهرست مراجع افزوده شود |  | 1402-2294-228106 | 1402/06/08 | اعمال گردید
2 | پلاستر سیمان زیر پوشش MDF دیوار اعمال نشده است.لحاظ گردد |  | 1402-2294-228106 | 1402/06/08 | در جدول و وال سکشن اعمال گردید
3 | در خصوص عرض درب ورودی میبایست حداقل 110 سانتی متر لحاظ گردد |  | 1402-2294-228106 | 1402/06/08 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: