## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2015 |  |  | Transmital Date: 10.Apr.2023
Document Title: P&ID - 1st Stage Gas Compression Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2015 |  |  | Transmital Date: 10.Apr.2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D06 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بر اساس پاسخ ارائه شده توسط پیمانکار نقطه نظرات شماره 1 و 2 در CRS پیشین مورد تایید ایشان بوده و در ویرایش As Built اصلاح می گردد.. ضروریست پس از درج Tag No، سایز کلیه شیرها نیزدر کنار آن، درج گردد. |  | BK-SUR-ENG-PCS-02-07466 | 24.Apr.2023 | مورد تایید است.
2 | با توجه به مدارک سازنده، خط کنار گذز شیر Spill Back، و شیرهای مربوط به آن، نمایش داده شود. |  | BK-SUR-ENG-PCS-02-07466 | 24.Apr.2023 | پس از نهایی سازی نقشه های PID سازنده کمپرسور اعمال می گردد.
3 | مسیرهای Vent و Drain، برای همه Standpipe ها و LT های از نوع Displacer، در همه نقشه ها به صورت کامل نمایش داده شود. |  | BK-SUR-ENG-PCS-02-07466 | 24.Apr.2023 | عطف به صورتجلسه مورخ 1402/03/22 در خصوص بررسی و نهایی سازی مدارک مهندسی سطح الارض میدان بینک مقرر گردید ، شیرهای Vent و Drain، برای همه Standpipe ها و LT های از نوع Displacer در مدرک HOOK UP نمایش داده شود.
4 | برای شیر XV-2121 A، عبارت TSO از روی شیر یکطرفه حذف و زیر عبارت FC، درج گردد. |  | BK-SUR-ENG-PCS-02-07466 | 24.Apr.2023 | اصلاح گردید.
5 | جهت Reducer های قبل از شیر ایمنی اصلاح گردد. |  | BK-SUR-ENG-PCS-02-07466 | 24.Apr.2023 | اصلاح گردید.
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-02-07466 | 24.Apr.2023 | اعمال می‌گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021