## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0020 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2016 |  |  | Transmital Date: 10.Apr.2023
Document Title: P&ID - LP Flare System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2016 |  |  | Transmital Date: 10.Apr.2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D06 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مسیرهای Vent و Drain، برای همه Standpipe ها و LT های از نوع Displacer، در همه نقشه ها به صورت کامل نمایش داده شود. |  | BK-SUR-ENG-PCS-02-07467 | 24.Apr.2023 | عطف به صورتجلسه مورخ 1402/03/22 در خصوص بررسی و نهایی سازی مدارک مهندسی سطح الارض میدان بینک مقرر گردید ، شیرهای Vent و Drain، برای همه Standpipe ها و LT های از نوع Displacer در مدرک HOOK UP نمایش داده شود.
2 | نظر پیشین: فرمان remote start از DCS به MCC برای P-2201 نمایش داده شود. پاسخ ارائه شده توسط پیمانکار ارتباطی به نقطه نظر ارائه شده نداشته و این مورد صرفا تناقض درونی مدرک می باشد که می بایست رفع گردد. |  | BK-SUR-ENG-PCS-02-07467 | 24.Apr.2023 | اصلاح گردید.
3 | جهت Strainer ها اصلاح گردد. |  | BK-SUR-ENG-PCS-02-07467 | 24.Apr.2023 | اصلاح گردید.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-02-07467 | 24.Apr.2023 | مورد تایید است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: