## SHEET 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0025_D06 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2255 |  |  | Transmital Date: 22/Jul/2023
Document Title: Mechanical Data Sheets For Potable Water Pump |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0205-ME-TR-T-2255 |  |  | Transmital Date: 22/Jul/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0025_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به تغییر تیم مهندسی پروژه ضروری است سوابق نفرات جدید و چارت مهندسی مجدداً ارسال گردد.به عنوان نمونه در حالیکه آقای آدینه مدت زمان طولانی است با پیمانکار قطع همکاری نموده است اما همچنان مدارک با نام ایشان ارسال می گردد. |  | 02/2294/188041 | 1402/02/05 | چارت مهندسی بخش مکانیک متعاقباً ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: S.Zafaresmaeili | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 9/13/2023