## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-CN-000-D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2281 |  |  | Transmital Date: 8/1/2023
Document Title: Calculation Note For Line Sizing |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-2281 |  |  | Transmital Date: 8/1/2023
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PR-CN-0005-D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شماره خطوط مندرج در مدرک ارسالی می بایست با مدرک PID یکسانسازی بعمل آید به عنوان مثال می توان به دو خط ذیل اشاره نمود: LINE NO:GAS-111-0036A-CN05-6"-PT LINE NO:GAS-111-0037A-CN05-6"-PT |  | 1402-2294-228176 | 1402/06/08 | بر اساس آخرین تغییرات مدارک PID مدرک فوق بروز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021