## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-AR-DW-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2258 |  |  | Transmital Date:2023/7/23
Document Title: Architectural Drawing For Chemical Inj. Packages/Chemical Storage Shelter |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0004-AR-T-2258 |  |  | Transmital Date: 2023/7/23
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0004_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک ارسالی دیتا شیت فاقد اندازه تجهیزات میباشد.اصلاح گردد |  | 1402-2294-220124 | 1402/06/04 | ابعاد درنظر گرفته شده برای سایبان، متناسب با نیازمندی مربوطه می باشد. در این خصوص نقشه GA اولیه وندور، ضمیمه ریپلای شیت می گردد. شایان ذکر است مسؤولیت تغییرات احتمالی نیز برعهده این پیمانکار خواهد بود.
2 | با عنایت به تغییررخ داده در مساحت این شلتر مقتضی است به همراه ویرایش آتی مدرک فرم CRوتبعات مالی زمانی نیزارسال کردد بدیهی است تایید این مدرک منوط به تایید تغییر در کمیته تغییرات میباشد. |  | 1402-2294-220124 | 1402/06/04 | فرم C/R برای کلیه تغییرات مساحتی ابنیه GCS، متعاقبا و به صورت تجمعی ارائه می گردد.
22 | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
23
24 | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
25 | Commented By: | Signature |  |  |  | Clarified By: | Signature
26
Legend | Date: |  |  |  |  | Date:
Signature