## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0005_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1703 |  |  | Transmital Date: 17 Dec 2022
Document Title: Panels & Junction Box List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1703 |  |  | Transmital Date: 17 Dec 2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | برای خشک کننده ها هر کدام پنل کنترلی مستقل در نظر گرفته شود |  | 01/2294/388761 | 1401/10/13 | با توجه به آخرین نسخه مدارک Control/ESD/F&G System Block Diagram و Control Room Layout & Arrangement Drawing و ESD I.O List و DCS I.O List بروز رسانی گردید
2 | برای مجموعه فراِیندی نمزدا مانعی ندارد از سیستم کنترل TYPE B استفاده گردد ولی برای گرمکن پکیج نمزدا لازم است مطابق استاندارد های ایمنی از پنل کنترلی مستقل با شرایط استانداردی استفاده گردد |  | 01/2294/388761 | 1401/10/13 | با توجه به آخرین نسخه مدارک Control/ESD/F&G System Block Diagram و Control Room Layout & Arrangement Drawing و ESD I.O List و DCS I.O List بروز رسانی گردید
3 | مدرک پس از نهای سازی مدارک سازندگان پکیج های مختلف بروز رسانی گردد |  | 01/2294/388761 | 1401/10/13 | ملاحظه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 1 Jan 2023 |  |  |  |  | Date: