## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0005_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1703 |  |  | Transmital Date: 17 Dec 2022
Document Title: Panels & Junction Box List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1703 |  |  | Transmital Date: 17 Dec 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  |  | 2023-01-01 | ملاحظه گردید
2 | آيتم 4 مطابق توافقات صورت گرفته در نظر گرفته شود. (پنل براي هر Train بصورت مجزا) |  |  | 2023-01-01 | درخواست کارفرمای محترم اعمال گردید
3 | براي نيتروژن 2 پنل در نظر گرفته شود. |  |  | 2023-01-01 | مطابق مدرک Control Rom Layout & Arrangement Drawing برای پکیچ نیتروژن 2 تابلو در نظر گرفته شده است
4 | لوكيشن براي تمامي مدارك همسان سازي شود. Technical room اصلاح شود. |  |  | 2023-01-01 | درخواست کارفرمای محترم اعمال گردید
5 | تعداد I/O ها نهايي نيست و در صورت تغيير در اين مدرك منعكس شود. |  |  | 2023-01-01 | با آخرین نسخه I/O این مدرک بروز رسانی گردید
6 | تاييد گردد كه محل قرارگيري سيستم HVAC در اتاق تكنيكال مي باشد. |  |  | 2023-01-01 | محل قرارگيري سيستم HVAC در اتاق تكنيكال مي باشد.
7 | PA/GA Panel اضافه گردد |  |  | 2023-01-01 | درخواست کارفرمای محترم اعمال گردید
8 | مسئوليت تمامي تناقضات بين اين مدرك و مدارك وابسته مانند Terminal Diagram و Block Diagram بر عهده پيمانكار مي باشد. |  |  | 2023-01-01 | ملاحظه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 1 Jan 2023 |  |  |  |  | Date: