## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W018S-PEDCO-110-IN-MR-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2104 |  |  | Transmital Date: 15 May 2023
Document Title: PMR For WHCP/HPU - W018S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-2104 |  |  | Transmital Date: 15 May 2023
[5 empty] | CRS No: PEDCO-CRS-BK-W018S-PEDCO-110-IN-MR-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار است. |  | BK-SUR-ENG-INS-02-07750 | 2023-05-29 | نظرات اصلی کارفرمای محترم در مراحل فنی خرید و در حین انجام تست FAT نهایی گردیده است. از آنجایی که مدرک توسط کارفرمای اصلی تایید شده است و تجهیز مرتبط با این PMR نیز خریداری و تحویل داده شده است مدرک تنها با به روز رسانی مدارک فنی ضمیمه، FI گردید . نظرات آن کارفرمای محترم در تهیه سایر مدارک در نظر گرفته خواهد شد.
2 | با توجه به كامنت كارفرما بر روي مدرك در خصوص عبارت Purchaser، بنظر مي رسد كه توضيحات ارائه شده با EPC Contractor شباهت دارد. در اين خصوص شفاف سازي گردد و كامنت بخش QA/QC براي بند 6 در نظر گرفته شود. |  | BK-SUR-ENG-INS-02-07750 | 2023-05-29
3 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-INS-02-07750 | 2023-05-29
4 | در بند 5.1.2 ، بعد از عنوان مدرك Project spare part supply procedure ، شماره مدرك نيز بصورت E&C-QC-SP-1 وارد گردد. |  | BK-SUR-ENG-INS-02-07750 | 2023-05-29
5 | كلمات VENDOR و SUPPLIER در مدرك يكسان سازي شده و مطابق توضيحات بخش GENERAL DEFINITION از كلمه VENDOR استفاده گردد ( هرجا كه منظور شركت كاردانان شرق ميباشد) |  | BK-SUR-ENG-INS-02-07750 | 2023-05-29
6 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-INS-02-07750 | 2023-05-29
7 | The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT and EPC/EPD CONTRACTOR before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification.
8 | در بند (PRICE BREAKDOWN) ، در آيتم هاي شماره 2,3 ، شماره مدرك بصورت صحيح E&C-QC-SP-1 وارد گردد. |  | BK-SUR-ENG-INS-02-07750 | 2023-05-29
9 | درجدول Attachment 1 شماره مدرك دستورالعمل تامين قطعات يدكي بصورت صحيح E&C-QC-SP-1 آورده شود. |  | BK-SUR-ENG-INS-02-07750 | 2023-05-29
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari M.Torkaman | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 29 May 2023 |  |  |  |  | Date: