## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-LI-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1753 |  |  | Transmital Date:1/2/2023
Document Title: Relief Load Summary |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1753 |  |  | Transmital Date:1/2/2023
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PR-LI-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بر اساس نظر شرکت توسعه پترو ایران، نیازی به در نظر گرفتن سناریوهای Blocked outlete و Fire برای توپکران و توپک گیر نمی باشد و در نظر گرفتن TSV کافیست.. ضروریست این مورد درجلسات مشترک با ذینفع اصلی پروژه مطرح شده و تایید ایشان در این خصوص اخذ گردد. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | بازگشت به مذاکرات شفاهی با کارفرمای اصلی پروژه (NISOC) مقرر گردید مطابق مدارک طراحی پایه بر روی تجهیزات PL و PR شیرهای ایمنی PSV در نظر گرفته شود.
2 | برای بررسی اطلاعات فرايندي ضروریست فایلهای شبیه سازی به پیوست ارسال گردد. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | فایل شبیه سازی به پیوست ارسال می گردد.
3 | ضروريست است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-06766 | 2023-01-24 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021