## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PL-CN-0001-D03 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: CALCULATION NOTE FOR PIPELINE WALL THICKNESS |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PL-CN-0001-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | محاسبه ی ضخامت فقط برای سایز های درج شده در P&ID ارائه شود. |  |  | 1402/03/23 | نقطه نظر کارفرمای محترم اعمال گردید.
2 | فشار طراحی برای خطوط گاز 8 اینچ ،1350psi در نظر گرفته شده و محاسبات برای design factor طراحی0.6 و 0.72 ارائه میگردد. |  |  | 1402/03/23 | نقطه نظر کارفرمای محترم اعمال گردید.
3 | برای کلاس CN15 فشار طراحی 46.5 بار معادل 675psi در نظر گرفته شده و محاسبه ی ضخامت برایdesign factor های 0.6 و 0.72 در نظر گرفته شود. |  |  | 1402/03/23 | نقطه نظر کارفرمای محترم اعمال گردید.
4 | مقرر گردید مدرک PMS خط لوله براساس موارد فوق اصلاح گردد. |  |  | 1402/03/23 | نقطه نظر کارفرمای محترم اعمال میگردد.
5 | مقرر گردید موارد غیر ضروری از جمله روش محاسبات براساس استانداردASME B31.1 از مدرک حذف شود. |  |  | 1402/03/23 | استاندارد اعلامی در مدرک ارائه نشده است.
6 | مقرر گردید در مدرک اکسل محاسبات طراحی ضخامت یک شیت اضافه گردد و فرمول محاسبات خوردگی و محاسبات مربوطه و جداول استانداردی درج گردد. |  |  | 1402/03/23 | فرمول محاسبات در ابتدای مدرک ارائه شده است. لطفا به فایل PDF مراجعه شود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
Date: