## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PL-CN-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1694 |  |  | Transmital Date:12/26/2022
Document Title: Calculation Note For Pipeline Wall Thickness |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PL-TR-1694 |  |  | Transmital Date:12/26/2022
[5 empty] | CRS No: CRS-BK-PPL-PEDCO-320-PL-CN-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص خطوط پایین تر از 8 اینچ در کلاس FN27 ضریب طراحی مطابق با شرایط سایت اصلاح گردد. |  | 1401/2294/427550 | 1401/11/09 | مطابق صورتجلسه برای سایزهای پایین 0.6 در نظر گرفته شد و برای 8 اینچ با صریب 0.6 و 0.72 محاسبه گردید.
2 | در خصوص خطوط پایین تر از 4 اینچ در کلاس CN15 ضریب طراحی مطابق با شرایط سایت اصلاح گردد. |  | 1401/2294/427550 | 1401/11/09 | مطابق صورتجلسه برای سایزهای پایین 0.6 در نظر گرفته شد و برای 4 اینچ با صریب 0.6 و 0.72 محاسبه گردید.
3 | .ضریب طراحی خط 6 اینچ در کلاس CN15 اصلاح شود. |  | 1401/2294/427550 | 1401/11/09 | با توجه به این که محاسبه ی ضخامت فقط برای سایز های درج شده در P&ID ارائه شده است حذف گردید.
4 | مدرک PMS مربوطه متناسب با مندرجات این مدرک به روز رسانی و اصلاح شود. |  | 1401/2294/427550 | 1401/11/09 | نقطه نظر کارفرمای محترم اعمال میگردد.
5 | روش انجام محاسبات مربوط به ضخامت در مدرک بیان گردد. |  | 1401/2294/427550 | 1401/11/09 | در ایتدای مدرک عتوان شده است و فایل محاسبات به صورت اکسل ارائه شده است که در انتهای فایل PDF نیز ارائه می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 13/03/2022 |  |  |  |  | Date: 13/03/2022