## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-SSGRL-PEDCO-110-PL-SP-0001_D04 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: PIPELINE MATERIAL SPECIFICATION |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date:
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مقرر گردید در مدرک PIPELINE WALL THICKNESS CALCULATION، نوت اصلاح شده در مدرک مطالعات خوردگی مربوطه درج گردد. |  |  | 1402/03/23 | نقطه نظر کارفرمای محترم در D04 اعمال شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
Date: