## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PL-CN-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1694 |  |  | Transmital Date: 12/26/2022
Document Title: Calculation Note For Pipeline Wall Thickness |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PL-TR-1694 |  |  | Transmital Date: 12/26/2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PL-CN-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در صورتي كه كاهش ضخامت خطوط لوله 8 اينچ گاز و 4 اينچ كاندنسيت نسبت به مهندسي پايه مورد تأييد ذينفع اصلي پروژه قرار گيرد نقطه نظر خاصي مطرح نمي باشد. در صورت تأييد ذينفع اصلي پروژه نسخه AFC ارسال گردد. |  | BK-SUR-ENG-PPL-01-05442 | 2022-08-15 | احتراما پیرو کامنت کارفرمای محترم در مدرک BK-PPL-PEDCO-320-PL-SP-0001 ضخامت خط لوله 8 اینچ گاز اصلاح شد. |  |  | See Item 3
2 | مطابق نظر ذينفع اصلي در بخش 3.1 ويرايش 3 براي استاندارد IPS-M-PI-190 درج گردد. |  | BK-SUR-ENG-PPL-01-05442 | 2022-08-15 | احتراما نقطه نظر اعمال گردید. |  |  | CLOSED
3 | در كلاس CN15 ضخامتهاي انتخابي براي خطوط لوله مطابق IPS نبايستي كمتر از 4.8mm باشد. |  | BK-SUR-ENG-PPL-01-06412 | 2022-12-17 | احتراما نقطه نظر اعمال گردید. |  |  | CLOSED
4 | در این برهه نقطه نظر خاصی مطرح نمی باشد. از این رو پیشبرد گام بعدی مهندسی بلامانع است. شایان ذکر است با توجه به مفاد 13 شرایط عمومی پیمان, مسئولیت هر نوع نقص و کمبود در نقشه ها و مدارک و مشخصات فني و سفارش كالا در محدوده پروژه و در هر مقطع از پروژه بر عهده پیمانکار است. |  | BK-SUR-ENG-PPL-01-06535 | 2022-12-26
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 26/12/2022 |  |  |  |  | Date: 26/12/2022