## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PL-CN-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1517 |  |  | Transmital Date:10/19/2022
Document Title: PIPELINE WALL THICKNESS CALCULATION |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PL-TR-1517 |  |  | Transmital Date:10/19/2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شایان ذکر است که اظهار نظر نهایی در خصوص این مدرک منوط به تایید مدرک مطالعات خوردگی و تعیین میزان C.A خواهد بود. |  | 1401-2294-329912 | 2022-11-27 | مدرک مورد نظر در نسخه ی D06 ارسال و توسط کارفرمای محترم تایید شده است.
2 | مقرر گردید در مدرک PIPELINE WALL THICKNESS CALCULATION، نوت اصلاح شده در مدرک مطالعات خوردگی مربوطه درج گردد. |  | صورتجلسه | 1402/03/23 | نقطه نظر کارفرمای محترم در D03 اعمال شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 13/03/2022 |  |  |  |  | Date: