## Sheet1
N.I.S.O.C |  | Transmital Date:3/6/2023+K14:P20
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0010-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1943 |  |  | Transmital Date:3/6/2023
Document Title: SPECIFICATION FOR PLANT PIPING SYSTEMS PRESSURE TESTING |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR- 1943 |  |  | Transmital Date:3/6/2023
[5 empty] | CRS No: NISOC-PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0010_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | توضیحات مندرج در Reply Sheet مورد پذیرش نمی باشد.همانگونه که بارها بیان شده است در صورت بروز هرگونه تغییر به هر نحو میبایست دلایل بروز آن در Reply Sheet بیان گردد. |  | 1402-2294-11564 | 2023-04-05 | مطابق صورتجلسه مدرک اصلاح گردید.
2 | هرگونه بحث فنی بایستی پیش از انتشار نسخه AFC یا AFD نهایی گردد و از انتشار شتابزده و بی پشتوانه ی مدارک مهندسی پرهیز شود تا نیاز به بازنگری و بیان انحرافات در مراحل بعدی نداشته باشد. |  | 1402-2294-11564 | 2023-04-05 | مطابق صورتجلسه مدرک اصلاح گردید.
3 | بند 6,9,8 از مدرک حذف شود. |  | 02/2294/11564 | 2023-04-05 | نقطه نظر کارفرمای محترم اعمال گردید.
4 | منظور از کلمه ی Company در بند 6,9,9 مشخص نیست. |  | 02/2294/11564 | 2023-04-05 | نقطه نظر کارفرمای محترم اعمال گردید.
5 | در جدول ANNEX 1 آیتم 2 از TEST NO به TEST PACKAGE NO. تغییر یابد. |  | صورتجلسه | 1402/03/23 | نقطه نظر کارفرمای محترم اعمال گردید.
6 | یک ستون برای WATER QUALITY CERTIFICATIONاضافه گردد. |  | صورتجلسه | 1402/03/23 | نقطه نظر کارفرمای محترم اعمال گردید.
7 | آیتم های 7و8 به TEST START TIME و TEST COMPLETED TIME تغییر کند. |  | صورتجلسه | 1402/03/23 | نقطه نظر کارفرمای محترم اعمال گردید.
8 | آیتم شماره 9 از REMARK به RESULT تغییر کند. |  | صورتجلسه | 1402/03/23 | با توجه به ستون اضافه شده برای WATER QUALITY CERTIFICATION تغییر در آیتم شماره10 اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.mousazadeh | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date:18-Dec.-2022 |  |  |  |  | Date: