## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-CN-0026 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2193 |  |  | Transmital Date:1402/03/22
Document Title: Calculation Note for Chemical Injection and Storage Shelter |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0026-ST-T-2193 |  |  | Transmital Date:1402/03/22
[5 empty] | CRS No:NISOC-CRS- BK-GCS-PEDCO-120-ST-CN-0026_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-182130 | 2023-07-30 | مورد تایید است .
2 |  |  | 1402-2294-182130 | 2023-07-30 | مورد تایید است .
3 |  |  | 1402-2294-182130 | 2023-07-30 | مورد تایید است .
4 |  |  | 1402-2294-182130 | 2023-07-30 | مورد تایید است .
5 |  |  | 1402-2294-182130 | 2023-07-30 | مورد تایید است .
6 |  |  | 1402-2294-182130 | 2023-07-30 | مورد تایید است .
7 |  |  | 1402-2294-182130 | 1402/05/08 | مورد تایید است .
8 |  |  | 1402-2294-182130 | 2023-07-30 | تغییرات مطابق با نقشه های معماری صورت پذیرفته است .
9 |  |  | 1402-2294-182130 | 2023-07-30 | اعمل گردید .
10 |  |  | 1402-2294-182130 | 2023-07-30 | اعمال گردید .
11 |  |  | 1402-2294-182130 | 2023-07-30 | جانمایی مطابق با پلات پلن انجام شده است .
12 |  |  | 1402-2294-182130 | 2023-07-30 | اعمال گردید .
13 |  |  | 1402-2294-182130 | 2023-07-30 | با توجه به ضخامت فنداسیون نیازی به FACE BAR نمی باشد .
14 |  |  | 1402-2294-182130 | 2023-07-30
15 |  |  | 1402-2294-182130 | 2023-07-30 | اعمال گردید .
16 |  |  | 1402-2294-182130 | 2023-07-30 | اعمال گردید .
17 |  |  | 1402-2294-182130 | 2023-07-30 | اعمال گردید .
18 |  |  | 1402-2294-182130 | 2023-07-30 | اعمال گردید .
19 |  |  | 1402-2294-182130 | 2023-07-30 | اعمال گردید .
20 |  |  | 1402-2294-182130 | 2023-07-30 | مورد قبول می باشد .
21 |  |  | 1402-2294-182130 | 2023-07-30 | تغییرات مطابق با نقشه های معماری صورت پذیرفته است .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: