## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-IN-MR-0007_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1984 |  |  | Transmital Date: 3/29/2023
Document Title: PMR FOR F&G DETECTOR- EXTENSION OF BINAK B/C MANIFOLD |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1984 |  |  | Transmital Date: 3/29/2023
[5 empty] | CRS No: NISOC-W007S-BK-GCS-PEDCO-110-IN-MR-0007_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک MR پس از تولید و نهایی شدن کلیه مدارک مهندسی تفصیلی مربوطه (مانند مشخصات فنی، داده برگ ها و MTO ...) می بایست تولید گردد، زیرا تمامی مدارک مذکور در مورد هر پکیج خرید، می بایست با درج ویرایش نهایی و عنوان آن در متن، ضمیمه MR ها شوند. |  | 02/2294/68122 | 2023-05-15 | با توجه به نظر کارفرمای محترم پیوست یک مدرک، مطابق آخرین مدارک موجود در پروژه اصلاح گردید.
2 | ساختار کلی مدرک مورد تایید بوده ، لیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی مدارک مرتبط مهندسی و درج نسخ تایید شده (AFC) است.معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق ، نهایی سازی مدارک پیش نیاز (که در پیوست 1 مدرک اشاره شده است) در دستور کار تیم مهندسی آن پیمانکار قرار گیرد. |  | 02/2294/68122 | 2023-05-15
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: