## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0019_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1980 |  |  | Transmital Date: 3/28/2023
Document Title: PMR For Level Transmitter - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1980 |  |  | Transmital Date: 3/28/2023
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0019_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تمامی مدارک پیش نیاز در مورد هر پکیج خرید، می بایست با درج ویرایش نهایی و عنوان آن در متن، ضمیمه MR ها شوند. |  | 1402/2294/65463 | 2023-05-14 | با توجه به نظر کارفرمای محترم ATTACHMENT 1 مدرک، مطابق آخرین مدارک موجود در پروژه اصلاح گردید.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: