## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0019_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1980 |  |  | Transmital Date: 3/28/2023
Document Title: PMR For Level Transmitter - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1980 |  |  | Transmital Date: 3/28/2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0019_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در صورت تغيير در هر كدام از مدارك پايه در اين مدرك نيز لحاظ گردد. |  | BK-SUR-ENG-INS-02-07369 | 2023-04-09 | ملاحظه گردید.
2 | تايپ ترانسميتر در نظر گرفته شده با P&ID و ديتاشيت تناقض دارد. موارد اصلاح گردد. |  | BK-SUR-ENG-INS-02-07369 | 2023-04-09 | مطابق دیتاشیت تهیه گردید.
3 | در مدرك عبارات Vendor Document Index and Schdule و VPIS يكسان سازي شود. |  | BK-SUR-ENG-INS-02-07369 | 2023-04-09 | اعمال گردید.
4 | در بند 6: -دستورالعمل شماره E&C-QC-IN-SP-1 حذف گردد. -بعد از دستورالعمل شماره ICE-EID-MI-SP01-، عبارت Rev01 اضافه گردد. |  | BK-SUR-ENG-INS-02-07369 | 2023-04-09 | اصلاح گردید.
5 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-INS-02-07369 | 2023-04-09 | اعمال گردید.
6 | در مدرك عبارات Vendor Document Index and Schdule و VPIS يكسان سازي شود. |  | BK-SUR-ENG-INS-02-07369 | 2023-04-09 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: