## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-MR-0003_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1818 |  |  | Transmital Date: 23-Jan-2023
Document Title: PMR For Existent MV Switchgear Expansion & RCP |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-1818 |  |  | Transmital Date: 23-Jan-2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-MR-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه برخی از مدارک قید شده در بخش اسناد مرجع هنوز نهایی نشده است، مقتضی است آخرین ویرایش مدارک تأیید شده در بخش مراجع قید گردد. |  | 1401-2294-454879 | 2023-02-19 | مدارک مورد نیاز در لیست مراجع در نظر گرفته خواهد شد. در صورت تغییر در هر مدرک ، این MR می بایست متعاقبا مورد ویرایش قرار گیرد.
2 | در پوشه Native بخش Attachment برخی از مدارک مانند مدرک چیدمان تابلو در کلیدخانه گنجانده شده که می بایست پس از تأیید و نهایی شدن جایگزین گردند. |  | 1401-2294-454879 | 2023-02-19
| در جدول بخش General یک ستون با عنوان Unit ایجاد شده و برای تجهیزات مانند سوییچگیر واحد Setr تعریف گردد. |  | 1401-2294-454879 | 2023-02-19 | در این جدول ستونی با عنوان QTY وجود دارد که در آن تعداد تجهیزات مورد نیاز ذکر شده است. همچنین مطالب جدیدی به این جدول اضافه شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: