## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-LI-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2215 |  |  | Transmital Date: 6/20/2023
Document Title: I/O List For Control /ESD System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2215 |  |  | Transmital Date: 6/20/2023
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-LI-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-08030 | 2023-07-04 | ملاحظه گردید
2 | مشترك بودن مدرك I/O براي سيستم ESD و DCS منوط به تاييد كارفرما مي باشد. |  | BK-SUR-ENG-INS-02-08030 | 2023-07-04 | مطابق MDL نسخه G10 (آخرین نسخه ) این مدرک بصورت مشترک ESD , DCS نهایی شده است
3 | با توجه به مدرك Config ارائه شده Push Button ها براي Solenoid ها (Open/Close ¦ ESD) بعنوان ورودي به سيستم در نظر گرفته شود. |  | BK-SUR-ENG-INS-02-08030 | 2023-07-04 | Push Buttom ها بروی تابلو ( ESOV-3202 ) تحت عنوان سیگنال خروجی از سیستم به سمت ولو ارسال می گردند.
4 | IS و NIS بودن Relay ها مشخص گردد. |  | BK-SUR-ENG-INS-02-08030 | 2023-07-04 | درخواست کارفرمای محترم اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: