## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DG-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1613 |  |  | Transmital Date: 11/27/2022
Document Title: Instrument Hook-up Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR- 1613 |  |  | Transmital Date:11/27/2022
[5 empty] | CRS No: PEDCO-CRS- BK-W007S-PEDCO-110-IN-DG-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-06398 | 2022-12-13 | ملاحظه شد
2 | شماتيك CC و CP براي Liquid نمايش داده شود. |  | BK-SUR-ENG-INS-01-06398 | 2022-12-13 | با توجه به محدودیت فضا مطابق توافقات انجام شده در مدل سه بعدی و مدرک DATA SHEET نصب CC و CP برای GAS و LIQUID مشابه هم در موقعیت ساعت 12 می باشد .توضیحات در مدرک HOOK UP اصلاح شد.
NEW COMMENTS
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-07681 | 2023-05-22 | ملاحظه گردید.
2 | كامنت هاي بخش ابزاردقيق بپيوست ارائه مي گردد. |  | BK-SUR-ENG-INS-02-07681 | 2023-05-22 | مشاهده و پاسخ داده شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 22 May 2023 |  |  |  |  | Date: