## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W028-PEDCO-110-PI-MR-0008_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1935 |  |  | Transmital Date: 06-May-2023
Document Title: PMR FOR STONE TRAP– W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR- 1935 |  |  | Transmital Date: 06-May-2023
[5 empty] | CRS No: PEDCO-CRS-BK-W028-PEDCO-110-PI-MR-0008_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عبارت " List of Documents Will be Finalized in Vendor Document index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-PIP-01-04122 | 2022-02-05 | احتراما در ویرایش D01 مدرک اعمال می گردد. |  |  | Closed
2 | نوت داده شده، در انتهاي جدول پيوست 2، آورده شود. |  | BK-SUR-ENG-PIP-01-07169 | 2023-12-03 | احتراما در ویرایش D02 مدرک اعمال می گردد. |  |  | Closed
3 | در بند 6: -عبارت "QC Plan" و "Quality Control Plan" به "Inspection and Test Plan (ITP)" تغيير يابد. |  | BK-SUR-ENG-PIP-01-07169 | 2023-12-03 | احتراما در ویرایش D02 مدرک اعمال می گردد. |  |  | Closed
4 | در جدول پيوست 1، مدرك Packing, Marking, Transportation Procedure اضافه گردد. |  | BK-SUR-ENG-PIP-01-07169 | 2023-12-03 | احتراما در ویرایش D02 مدرک اعمال می گردد. |  |  | Closed
5 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-PIP-01-07169 | 2023-12-03 | احتراما در ویرایش D02 مدرک اعمال می گردد. |  |  | Closed
6 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-PIP-02-07716 | 2023-05-27 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT/EPC CONTRACTOR before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification.
7 | در Attachment 1 ، مدرك دستورالعمل تامين قطعات يدكي راه اندازي و راهبري دو سالانه E&C-QC-SP-1 اضافه گردد |  | BK-SUR-ENG-PIP-02-07716 | 2023-05-27 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
8 | در بند 5.1.3 موارد زير اضافه گردد : 1. ذكر گردد كه گواهينامه متريال بر اساس BS EN 10204 / ISO 10474, Type 3.2 certificate (or certificates) باشد. 2. All Materials specified with NACE shall meet the requirements of Sour Services. Sour services’ materials shall meet the requirement of NACE MR0175/ISO 15156 standard. |  | BK-SUR-ENG-PIP-02-07716 | 2023-05-27 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
9 | علاوه بر كامنتهاي فوق كه در ويرايش بعدي بايستي برطرف گردد. به اطلاع مي رساند مدرك MR پس از توليد و نهايي شدن كليه مدارك مهندسي تفصيلي مربوطه( مانند مشخصات فني، داده برگ ها و PMS ) مي بايست توليد گردد.چرا كه تمامي مدارك مذكور در مورد هر پكيج خريد، مي بايست با درج ويرايش نهايي و عنوان آن در متن،ضميمه MR ها شوند. لذا از آنجا كه مدارك پيش نياز اين مدرك هنوز نهايي نشده است تائيد نهايي اين مدرك پس از نهايي شدن مدارك مذكور مقدور مي باشد. |  | BK-SUR-ENG-PIP-02-07716 | 2023-05-27 | نظر کارفرمای محترم مد نظر قرار می گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri/J.Mosazadeh M. Torkaman | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date:27/05/2023 |  |  |  |  | Date:27/05/2023