## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-CV-PY-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1866 |  |  | Transmital Date: 2/14/2023
Document Title: Plant Underground Composite Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1866 |  |  | Transmital Date: 2/14/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-CV-PY-0006_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بخش برق 1- چیدمان تجهیزات برقی از جمله ترانسفورماتورهای برق پروژه و مکان جدید دیزل ژنراتور اضطراری بر اساس توافقات انجام شده می باسیت اصلاح گردد. |  | 1401-2294-485393 | 1401/12/20 | این مطلب در حیطه مسئولیتهای بخش سیویل نمیباشد.
2 | 2- پیرو نامه شماره 172867 مورخ 1401/05/20 (پاسخ ترانسمیتال TR-1159) نوع ترانشه های کابل در محوطه داخل فنس بصورت بتنی و در خارج از فنس بصورت دفنی خاکی خواهد بود. |  | 1401-2294-485393 | 1401/12/20 | براساس توافقات دیسیپلین برق با کارفرمای محترم، ترنچها در محوطه بتنی، بتنی بوده و در محوطه های خاکی، خاکی است.
3 | بخش مکانیک 3- بررسی این مدرک پس از نهایی سازی پلات پلان میسر خواهد بود. |  | 1401-2294-485393 | 1401/12/20 | این مدرک بر اساس آخرین ویرایش مدرک پلات پلن تولید شده و درصورت تغییر پلات پلن در ویرایش های بعدی، این مدرک نیز به روز رسانی خواهد شد.
4 | نقطه نظر بخش فرآیند 4- ضروریست چیدمان تجهیزات پروژه بر اساس آخرین توافقات انجام شده می بایست صورت پذیرد. |  | 1401-2294-485393 | 1401/12/20 | این کامنت مربوط به مدرک پلات پلن است و مدرک سیویل براساس آخرین ویرایش تولید شده پلات پلن تولید میشود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: