## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W008N-PEDCO-110-PI-DG-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1522 |  |  | Transmital Date:10/22/2022
Document Title: Material Flow Diagram - W008N |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1522 |  |  | Transmital Date:10/22/2022
[5 empty] | CRS No:PEDCO-CRS-BK-W008N-PEDCO-110-PI-DG-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به مفاد صورتجلسه 1401/05/12 (نامه شماره 179119 مورخ 1401/05/24)،ضروریست در بخش توضیحات NOTE1 مدرک مطالعات خوردگی و انتخاب مواد (حد مجاز خوردگی واقعی بخش خط لوله ) اشاره شود. |  | 1401-2294-327300 | 1401/09/03 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 21-Nov-2021 |  |  |  |  | Date: 21-Nov-2021