## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-DG-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1522 |  |  | Transmital Date:10/22/2022
Document Title: Material Flow Diagram - W007S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1522 |  |  | Transmital Date:10/22/2022
[5 empty] | CRS No:PEDCO-CRS-BK-W007S-PEDCO-110-PI-DG-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | In The document Pipline corrosion study and Material Selection Report BK-SSGRL-PEDCO-110-PL-RT-0001-D04 Page 19 Para. 2 stated that "Corrosion Coupon shall be considered for flow line inlet" which is in conflict with the contractor Reply. If Cc, Cp not needed at wellheads the above sentence in the mentioned reference document shall be deleted. |  | BK-SUR-ENG-PIP-01-06052 | 2022-10-31 | نقشه های PID تجهیزات سرچاهی بر اساس مدارک طراحی پایه تهیه و تولید شده اند و از آنجا ییکه در نظر گرفتن CC و CP شامل تبعات مالی و زمانی می باشد لذا از منظر این پیمانکار تغییر طراحی پیش گفته ابتدا می بایست توسط ذینفع اصلی (NISOC) تایید و مراتب امر به ابلاغ گردد.
2 | In the latest Rev. of P&ID's (D04) in the Burn Pit line after Choke Flange the piping class is AN15 with CA=3mm. It shall be shown in Material Flow Diagrams after Choke flange of Burn pit line CS + 3mm CA + NACE. Also, after Stone Trap and before valve in the flow line the piping calss is LN17 so CS + 6mm CA + NACE shall be shown in the Material Flow Diagrams . |  | BK-SUR-ENG-PIP-01-06052 | 2022-10-31 | اعمال گردید.
3 | In the Refernce documents Pipline corrosion study and Material Selection Report BK-SSGRL-PEDCO-110-PL-RT-0001 referred that is belonged to Flowlines. the Piping corrosion study and Material Selection Report BK-SSGRL-PEDCO-110-PI-RT-0001 that is belonged to Wellhead shall be referred, too. |  | BK-SUR-ENG-PIP-01-06052 | 2022-10-31 | کامنت نامفهوم است. مدرک گفته شده (Piping corrosion study and Material Selection Report BK-SSGRL-PEDCO-110-PI-RT-0001 ) در مدرک به عنوان مرجع آورده شده است.
4 | Note 1 mentioned in the document is incorrect, it shall be changed as follows: 1- WALL THICKNESS SHALL BE IN ACCORDANCE WITH WALL THICKNESS CALCULATION REPORT. |  | BK-SUR-ENG-PIP-01-06052 | 2022-10-31 | اعمال گردید.
5 | Corrosion Monitoring requirements to be mentioned (CC, CP) |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | با توجه به نقشه های طراحی پایه و عدم درنظر گرفتن CC,CP در طراحی ذکر شده، نیازی به در نظرگرفتن تجهیزات فوق نمی باشد. همچنین بار مالی اضافه نمودن موارد فوق اگر از منظر کارفرما الزامی است ، مراتب را امر به ابلاغ فرمایید. |  |  | See Item 8
6 | Material comments will be finalized after updating corrosion study and Material Selection based on mentioned comments sent by Email BK-SUR-ENG-PPL-00-02059 dated 21-Nov-2021. |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | مدارک مربوطه برای کارفرما ارسال شده است. |  |  | See Item 8
7 | After finalizing P&ID's and Corrosion Study & Material Selection and the Client approval the comment will be closed |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | مورد تایید است |  |  | See Items 8 & 9
8 | Material comments will be finalized after updating corrosion study and Material Selection based on mentioned comments sent by Email BK-SUR-ENG-PIP-01-03917 dated 4/16/2022, BK-SUR-ENG-PPL-01-03705 dated 4/3/2022 and BK-SUR-ENG-PPL-00-03447 dated 3/12/2022. |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | رجوع شود به بند 2 فوق |  |  | See Items 8
9 | Material Flow Diagrams shall be in accordance with final P&ID's by identifying size and rating of all Valves and Stone Trap. It is better to identify all Instruments, too. |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | با توجه به ماهیت مدرک فوق از منظر این پیمانکار نیاز به اضافه نمودن تجهیزات ابزار دقیق و سایر تجهیزات موجود در PID نمی باشد. |  |  | Closed
10 | The document Piping corrosion study and Material Selection Report BK-SSGRL-PEDCO-110-PI-RT-0001 shall be referred, too. |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | مدرک اشاره شده در قسمت REFRENCE به عنوان ذکر شده است. |  |  | See Item 10
11 | Note 1 shall be changed as follows: 1- WALL THICKNESS SHALL BE IN ACCORDANCE WITH WALL THICKNESS CALCULATION REPORT. |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | مدارک مربوطه برای کارفرما ارسال شده است. |  |  | See Item 11
12 | تأييد اين مدرك منوط به تأييد نهايي مدارك مطالعات خوردگي BK-SSGRL-PEDCO-110-PL-RT-0001 و BK-SSGRL-PEDCO-110-PI-RT-0001 مي باشد. لازم است پيش از ارسال نسخه AFC اين مدرك، مدارك فوق تأييد شده باشند. |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | مدارک مربوطه برای کارفرما ارسال شده است.
13 | مدرك BK-SSGRL-PEDCO-110-PI-RT-0001 Piping corrosion study and Material Selection Report در جدول مرجع اضافه گردد. |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | نقطه نظر کارفرمای محترم اعمال گردید.
14 | كامنت كارفرما با مضمون "با توجه به مفاد صورتجلسه 1401/05/12 (نامه شماره 179119 مورخ 1401/05/24)،ضروریست در بخش توضیحات NOTE1 مدرک مطالعات خوردگی و انتخاب مواد (حد مجاز خوردگی واقعی بخش خط لوله ) اشاره شود" اعمال نگرديده است. |  | BK-SUR-ENG-PIP-01-06555 | 2022-12-28 | نقطه نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 21-Nov-2021 |  |  |  |  | Date: 21-Nov-2021