## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-BK12-PEDCO-110-AR-DW-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1917 |  |  | Transmital Date: 3/1/2023
Document Title: Architectural Drawing For Security Building of Well Pads - BK-12 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-TR-1917 |  |  | Transmital Date: 3/1/2023
[5 empty] | CRS No: NISOC-CRS-BK-BK15-PEDCO-110-AR-DW-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق با قرارداد مساحت ساختمان Guard House می بایست حداقل 42 مترمربع باشد که در مدارک ارسالی مساحت کمتری لحاظ شده است، بازنگری و اصلاح گردد. |  | 1401-2294-5332 | 1402/01/08 | مساحت افزایش یافت.
2 | عرض فضای اتاق 101 (اتاق استراحت) به حداقل 3 متر افزایش یابد. |  | 1401-2294-5332 | 1402/01/08 | عرض اتاق افزایش یافت.
3 | فن سرویس بهداشتی در بالای درب ورودی سرویس (بالای تراز 2.60) لحاظ گردد و در نمای مربوطه نمایش داده شود. |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
4 | درب ورودی به اتاق استراحت از نوع چوبی ABS با عرض یک متر لحاظ گردد. |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
5 | یک دیتایل کامل از مقطع عرضی دیوار (وال سکشن) به همراه کلیه جزییات ارائه گردد. |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
6 | سنگ قرنیز فضای اتاق 100 از 10 سانتیمتر به حداقل 110 سانتیمتر با سنگ گرانیت اصلاح گردد. |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
7 | به جدول نازک کاری ردیف بام نیز با لحاظ مشخصات مربوطه اضافه گردد. |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
8 | در محورهای 1و2 مابین محور Bتا C در محل فصل مشترک پنجره با درب ورودی، وال پست در نظر گرفته شود. |  | 1401-2294-5332 | 1402/01/08 | وال پست در نظر گرفته شد.
9 | برای کلیه دیوارهایی که سفیدکاری و رنگ آمیزی می گردد بایستی زیر لایه سفیدکاری، یک لایه پلاستر ماسه سیمان لحاظ گردد. جدول نازک کاری اصلاح گردد. |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
10 | در کلیه نماها و سکشنها تراز ارتفاعی روی پیاده رو درج گردد. |  | 1401-2294-5332 | 1402/01/08 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: