## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0007_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1568 |  |  | Transmital Date: 31/OCT/2022
Document Title: Mechanical Data Sheets For Diesel Oil Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1568 |  |  | Transmital Date: 31/OCT/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0007_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ابعاد مخزن ، HLL ، LL در صفحه 6 با آخرین ویرایش مدرک P&ID و اطلاعات وارد شده در جدول صفحه 4 همخواني ندارد. ضروری است یکسان سازی گردد. |  | BK-SUR-ENG-MEC-02-08280 | 2023-08-15 | نقطه نظرات اعمال شد
2 | با توجه به اصلاح نشدن مدرك و عدم ارسال براي ذينفع اصلي مي بايست پس از اعمال نقطه نظرات نسبت به جايگزيني مدرك بر روي همين ترانسميتال اقدام نماييد. |  | BK-SUR-ENG-MEC-02-08280 | 2023-08-15 | نقطه نظرات کارفرما ملاحظه و پاسخ داده شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 08/15/2023 |  |  |  |  | Date: