## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-220-HV-PY-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2280 |  |  | Transmital Date: 7/31/2023
Document Title: Plumbing & Sewage Piping Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-HV-TR-2280 |  |  | Transmital Date: 7/31/2023
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-220-HV-PY-0001_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تراز اجرایی لوله کشی آب سرد و گرم مصرفی مشخص گردد. |  | 1402-2294-255609 | 1402/07/01 | اعمال گردید.
2 | محل قرار گرفتن شیرهای قطع و وصل نا مناسب می باشد. |  | 1402-2294-255609 | 1402/07/01 | با توجه به لزوم امکان دسترسی به شیرآلات قطع و وصل در نقاط و محل های عمومی، شیرآلات قطع و وصل جانمایی شده اند.
3 | پیشنهاد می گردد جهت بررسی دقیق نقشه ها جزئیات غیر لازم حذف گردد. به عبارتی روی پلان خام شده معماری، نقشه تاسیسات ترسیم شود. |  | 1402-2294-255609 | 1402/07/01 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: