## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2322 |  |  | Transmital Date: 29/AUG/2023
Document Title: PMR For Instrument/Plant Air & Nitrogen Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0206-ME-TR-2322 |  |  | Transmital Date: 29/AUG/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0006_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
QC/QA COMMENTS:
1 | در اين برهه نقطه نظر خاصي مطرح نمي باشد . صرفا مي بايست نظرات احتمالي ذينفع اصلي پروژه بر روي اين مدرك اعمال گردد. همچنين لازم به ذكر است كه مسئوليت بروزرساني ويرايش مدارك پيوست مندرج در اين مدرك ، پس از نهايي شدن آنها ، بر عهده آن پيماكار مي باشد. |  | BK-SUR-ENG-MEC-02-08355 | 2023-08-29 | نقطه نظر ذینفع اصلی پروژه بر روی مدرک اعمال گردید همچنین با توجه به اینکه مدارک پیوست تقریباً نهایی شده است لذا خواهشمند است جهت تسریع در امور خرید بررسی مدرک مذکور در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: M.Fakharian | Signature
| Date : |  |  |  |  | Date: