## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-PY-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1996 |  |  | Transmital Date: 4/5/2023
Document Title: Area Lighting & Small Power Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0201-EL-TR-1996 |  |  | Transmital Date: 4/5/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-PY-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو نامه شماره 02/2294/55503 مورخ 1402/02/17 بخش سیویل در صورت مسقف شدن فضای بین محوطه کمپرسور ها، لازم است، مدرک بروزرسانی گردد. |  | 1402-2294-68311 | 1401/02/25 | محوطه کمپرسور در مدرک "BK-GCS-PEDCO-120-EL-PY-0004" نشان داده خواهد شد. در صورتیکه مطابق با مدرک سیویل تمام سقف پوشیده شود، مدرک مربوطه به روز خواهد شد.
2 | بند 5 Reply Sheet : در ضلع شمالی واحد جهت پخش نور بهتر، تعداد پایه از سه به چهار عدد افزایش پیدا کند. |  | 1402-2294-68311 | 1401/02/25 | مطابق با نظر کارفرمای محترم، تعداد پایه به چهار عدد افزایش یافت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: