## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DT-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1527 |  |  | Transmital Date: 10/22/2022
Document Title: Data Sheets For Pressure & Safety Relief Valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1527 |  |  | Transmital Date: 10/22/2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-IN-DT-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | صفحه 4 ، NOTE16 و نیز صفحات 5 ,6 مینیمم دمای محیط اصلاح گردد |  | 1401-2294-310857 | 1401/08/23 | دمای محیط مطابق مدرک Process Basis Of Design در نظر گرفته شد.
2 | فشار عملیاتی PSV-3201 با آخرین ویرایش مدرک PFD پروژه همخوان نمی باشد یکسان سازی گردد |  | 1401-2294-310857 | 1401/08/23 | مطابق نظر کارفرمای محترم یکسان سازی صورت پذیرفت.
3 | در خصوص متریال اعلام شده تطابق مشخصات با PMS تائید شده الزامی است |  | 1401-2294-310857 | 1401/08/23 | کارفرمای محترم متریال مطابق مدرک PMS برای کلاس FN05 شیر سایز "2 معادل Ball اعلام شده است
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: