## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-LI-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1110 |  |  | Transmital Date: 6/22/2022
Document Title: Set Point & Alarm List |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date: 6/22/2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-LI-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به نهايي نبودن مدارك پيش نياز مانند P&ID، موارد در طول مهندسي تفصيلي بررسي خواهد شد. |  | BK-SUR-ENG- INS-01-05018 | 2022-07-06 | ملاحظه گردید.
2 | نوع ادوات ابزار دقيق مشخص گردد. |  | BK-SUR-ENG- INS-01-05018 | 2022-07-06 | اعمال گردید.
3 | مسئوليت تعداد ادوات از نظر مالي و زماني بر عهده پيمانكار فرعي مي باشد. |  | BK-SUR-ENG- INS-01-05018 | 2022-07-06 | ملاحظه گردید.
4 | در ستون LOCATION / PACKAGE NAME خط يا تجهيز مي بايست نوشته شود. |  | BK-SUR-ENG- INS-01-05018 | 2022-07-06 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: