## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0022_D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2066 |  |  | Transmital Date:07/May/2023
Document Title:Mechanical Data Sheets For Closed Drain Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2066 |  |  | Transmital Date:07/May/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D05 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند یک Reply sheet: نقطه نظرات این امور به طور کامل در مدرک اعمال نشده است، لازم است عبارت زیر در بخش General Note اضافه گردد. |  | 1402-2294-155378 | 1402/04/21 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است.
vendor shall fill in the blanks and return the complete data sheet along with motor data sheet Doc.No:BK-GCS-PEDCO-120-EL-DT-0008, With his proposal
2 | با توجه به شرایط، دلایل فنی در خصوص تغییر نوع پمپ مورد پذیرش بوده و ضروری است تبعات مالی/زمانی تعییرات ارسال گردد |  | 1402-2294-155378 | 1402/04/21 | فرم change request مربوطه به صورت مجزا ومتعاقباً ارسال خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M. Fakharian
| Date: |  |  |  |  | Date:10/7/2023