## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0024_D06 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2066 |  |  | Transmital Date: 07/May/2023
Document Title: Mechanical Data Sheets For Flare K.O. Drum Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2066 |  |  | Transmital Date: 07/May/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D05 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است در P&ID - LP Flare system نسبت به اصلاح كلاس فلنج و تطبيق آن با ديتا شيت اقدام شود. |  | BK-SUR-ENG-MEC-02-07565 | 2023-05-08 | .نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
2 | در مدارك محاسبات و ديتا شيت فرآيندي مربوطه بازه Density منعكس گردد. |  | BK-SUR-ENG-MEC-02-07565 | 2023-05-08 | .نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
3 | نقطه نظر خاصي مطرح نمي باشد صرفا ميبايست نقطه نظرات احتمالي كارفرما اعمال گردد. |  | BK-SUR-ENG-MEC-02-07565 | 2023-05-08 | .نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M.Fakharian
| Date: 5/8/2023 |  |  |  |  | Date: 9/13/2023