## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1508 |  |  | Transmital Date: 10/18/2022
Document Title: Process Data Sheets For 1st Stage G.C. Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1508 |  |  | Transmital Date: 10/18/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0002_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کامنت پیشین: در سايزينگ نازل ورودی اين تفكيكگر فرض بر وجود Vane pack شده است كه در اين مدرك لحاظ نشده است. اين عدم تطابق يا در اين مدرك يا در مدرك محاسبات مي بايست تصحيح گردد. |  | BK-SUR-ENG-PCS-01-06086 | 2022-11-06 | این مورد در مدرک برگه فنی و مدرک DRUM SIZING به روز رسانی گردید.
2 | کامنت پیشین: در شماتيك قطره گير از تجهيزات توزيع جريان در نازل ورودي استفاده شده در حاليكه در محل مورد نظر در مدرك اين مطلب گنجانده نشده است. نام تجهیز مورد نظر Inlet Flow diverter و یا Inlet Flow distributor بوده و Internal reinforcement نمی باشد. |  | BK-SUR-ENG-PCS-01-06086 | 2022-11-06 | اعمال گردید.
3 | نقطه نظرات ارائه شده در سايزينگ ظروف، در اين مدرك نيز اعمال گردد. |  | BK-SUR-ENG-PCS-01-06086 | 2022-11-06 | اعمال گردید.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06086 | 2022-11-06 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: