## PQS
|  |  | Procurement Quality Statistics FARVARDIN 1402) | [38 empty] | Doc. No.: | IMS-QC-FO-88-R0
[42 empty] | Rev No.: | 0
Rev Date.:
Item No. | Item Details | MR | TBE | P.O Status | MFG/ Vendor / Supplier |  | KOM (Kick-off meeting) | PIM (Pre Inspection Meeting) | TPI | CR Rating (Note 1) | KEY QUALITY DOCUMENTS | [14 empty] | INSPECTION STATUS | [12 empty] | FAT | IRN | IC | MDB / VDB / FDB | REMARKS
[5 empty] | Name | Location |  |  |  |  | MPS | QCP | ITP | Material Traceability / Serialization Procedure | WPS& PQR | NDT procedure |  |  |  |  | PWHT procedure | Hydrotest Procedure | Painting procedure | Specific Test Procedure (Note 2) | FAT procedure | MRI | Material Traceability | WQT Certificate | Fabrication Stage (Note 3) | Weld Traceability | VT / DT | NDT | PWHT | TQ / NCR |  | Hydrotest | Specific Test / Inspection (Note 4) | Final Inspection
[16 empty] | UT | RT | MT | PT | Hardness | [13 empty] | Issued No. | Closed No.
1 | WHCP | Issued and reviewed by QC | Issued and reviewed by QC and approved by client | Placed | کاردانان شرق | Mashhad | Done and Closed | Done and Closed | 2R | 2 | Approved | Approved | Approved | Approved | Approved | N/A | N/A | N/A | Approved | N/A | N/A | Approved | Approved | Approved | Approved | Done | Monitored | Issued | Dimentional ,Visual,NDT | N/A | Done | All Tests Completed But Partially Accepted | N/A | 0 | 0 | Done and Accepted | Done and Accepted | Done and Accepted | Done and Accepted | Issued and Accpepted | N/A | Not Issued
2 | Gas Compressors | Issued and reviewed by QC and approved by client | Issued and reviewed by QC and approved by client | Placed | هوایار | Karaj | Done and Closed | Done and Closed | 2R | 2 | Not issued | Not issued | Approved | Under Processing | Under Processing | Not issued | Not issued | Not issued | Not issued | Not issued | Not issued | Not issued | Not issued | Not issued | Not issued | Not Done | Not Monitord | Not Issued | Not Done | Not Monitord | Not Done | Under processing | Not Done | 0 | 0 | Not Done | Not Done | Not Done | Not Done | Not Issued | Not Issued | Not Issued
3 | Pipes 6" , 4" | Issued and reviewed by QC and approved by client | Issued and reviewed by QC | Placed | Hunan | China | Done and Closed | Done and Closed | 2R | 2 | Approved | Commented | Commented | Not issued | N/A | Not issued | N/A | Not issued | Not issued | Not issued | N/A | Not issued | Not issued | Not issued | N/A | Not Done | Not Monitord | Not Issued | Not Done | N/A | Not Done | Under processing | N/A | 0 | 0 | Not Done | Not Done | Not Done | N/A | Not Issued | Not Issued | Not Issued
4 | Pipes 8" | Issued and reviewed by QC | Issued and reviewed by QC | Placed | Hunan | China | Done but Not Closed | Done but Not Closed | 2R | 2 | Approved | Commented | Commented | Not issued | N/A | Not issued | N/A | Not issued | Not issued | Not issued | N/A | Not issued | Not issued | Not issued | N/A | Not Done | Not Monitord | Not Issued | Not Done | N/A | Not Done | Under processing | N/A | 0 | 0 | Not Done | Not Done | Not Done | N/A | Not Issued | Not Issued | Not Issued
5 | PIG Trap | Issued and reviewed by QC | Issued and reviewed by QC and approved by client | Placed | به کوش ویستا | Arak | Done and Closed | Done and Closed | 2R | 2 | Under Processing | Approved | Commented | Under Processing | Commented | Commented | Commented | Commented | Commented | N/A | Commented | Commented | Commented | Not issued | Not issued | Not Done | Not Monitord | Not Issued | Not Done | N/A | Not Done | Under processing | Not Done | 0 | 0 | Not Done | Not Done | Not Done | N/A | Not Issued | Not Issued | Not Issued
6 | Air Gas Cooler | Issued and reviewed by QC | Issued and reviewed by QC and approved by client | Placed | کولر هوایی آبان | Shiraz | Not Done | Not Done | 2R | 2 | Under Processing | Under Processing | Under Processing | Under Processing | Under Processing | Under Processing | Under Processing | Under Processing | Under Processing | Under Processing | Under Processing | Under Processing | Under Processing | Not issued | Not issued | Not Done | Not Monitord | Not Issued | Not Done | N/A | Not Done | Under processing | Not Done | 0 | 0 | Not Done | Not Done | Not Done | Not Done | Not Issued | Not Issued | Not Issued
10
11
12
13
14
15
Note 1: | Criticality rating refered to eqipment/comodity inspection level which is defined in specific procedures / client documents entitled with criticality assesment procedure or inspection level procedure.
Note 2: | Please specify procedure title.
Note 3: | Please specify the stage of fabrication at which test / inspection activities have been performed.
Note 4: | Please specify test / inspection title.
Abbreviation: MR: Material Requisition TBE: Technical Bid Evaluation PO: Purchase Order MFG: Manufacturer TPI: Third Party Inspector CR: Criticality MPS: Manufacturer Procedure Specification QCP: Quality Control Procedure ITP: Inspection Test Plan WPS: Welding Procedure Specification PQR: Procedure Qualification Record UT: Ultrasonic Test RT: Radiography Test MT: Magnetic Test PT: Penetration Test NDT: Non Destructive Test PWHT: Post Weld Heat Treatment FAT: Factory Acceptance Test MRI: Material Receive Inspection WQT: Welder Qualification Test VT: Visual Test DT: Dimension Test TQ: Technical Query NCR: Non Conformity Record IRN: Inspection Release Note IC: Inspection Certificate MDB: Manufacturer Data Book VDB: Vendor Data Book FDB: Final Data Book

## Sheet1 (hidden)
MR | TBE | PO | KOM/PIM | CR Rating | Document | MRI | Material Traceability | WQT Certificate | Weld Traceability | VT / DT | NDT | PWHT | TQ / NCR | Hydrotest | Final Inspection | FAT | IRN | IC | MDB/VDB
Issued and reviewed by QC | Scored by QC | Placed | Done and Closed | 1 | Under Processing | Done | Monitored | Issued | Monitored | Done | Under processing | Done and Accepted |  | Done and Accepted | Done and Accepted | Done and Accepted | Issued and Accpepted | Issued | Reviewed and Accepted
Issued but not reviewd by QC | Not scored by QC | Not Placed | Done but Not Closed | 2 | Not issued | Not Done | Not Monitord | Not Issued | Not Monitord | Not Done | All Tests Completed But Partially Accepted | Done But Not Accepted |  | Done But Not Accepted | Done But Not Accepted | Done But Not Accepted | Issued and Commented | Not Issued | Reviewed and Commented
Issued and reviewed by QC and approved by client |  |  | Not Done | 3 | Approved |  |  |  | N/A |  | All Tests Completed and Accepted | Not Done |  | Not Done | Not Done | Not Done | Not Issued | N/A | Under Review Processing
Issued but not reviewd by QC and approved by client |  |  |  | 4 | Approved With Comment | [5 empty] | N/A | N/A |  | N/A |  | N/A |  |  | Not Issued
Commented
Rejected
N/A

## CCS (hidden)
Item No. | Contractor | Discipline | KOM | MDR | PIM | Documentation Status | [21 empty] | Mat. Recd. Ins. |  | Construction | PWHT | Painting | Test |  |  | Precom. & Com. | FDB
[6 empty] | ITP |  | WPS/PQR |  | WQT |  | NDT |  | NDT Plan |  | Welding Map |  | Hydrotest |  | PWHT |  | Coating |  | SAT |  | Precom. & Com. |  | OPI | MIR |  |  |  | NDT | Hydrotest | SAT
[6 empty] | Issue Y/N | Status | Issue Y/N | Status | Issue Y/N | Status | Issue Y/N | Status | Issue Y/N | Status | Issue Y/N | Status | Issue Y/N | Status | Issue Y/N | Status | Issue Y/N | Status | Issue Y/N | Status | Issue Y/N | Status
1 |  | Civil
1.1 |  | Surveying
1.2 |  | Excavation
1.3 |  | Filling
1.4 |  | Compaction
1.5 |  | Reinforcing
1.6 |  | Concrete Pouring
1.7 |  | Road & Asphalt Paving
1.8 |  | Fencing
2 |  | Structure
2.1 |  | Erection
2.2 |  | Welding
2.3 |  | Bolt tightening
2.4 |  | Sandblast & Painting
3 |  | Architecture
4 |  | Pipeline
4.1 |  | Surveying
4.2 |  | Right of Way
4.3 |  | Excavation
4.4 |  | Stringing
4.5 |  | Assembling
4.6 |  | Welding
4.7 |  | Crossing
4.8 |  | Supporting/Bedding
4.9 |  | Coating
5 |  | Pipelaying
5.1 |  | Filling
5 |  | Piping
5.1 |  | Spool Fabrication
5.2 |  | Assembling
5.3 |  | Welding
5.4 |  | Supporting
5.5 |  | Coating
6 |  | Mechanic
6.1 |  | Foundation/Padding
6.2 |  | Erection
6.3 |  | Grouting
7 |  | Electrical
7.1 |  | Cable Tray and Conduit Installation
7.2 |  | Cable Installation
7.3 |  | Generator Installation
7.4 |  | Power Transformer Installation
7.5 |  | Bus Dust Installation
7.6 |  | HV/LV Switchgear and MCC Installation
7.7 |  | UPS and Battery Charger Installation
7.8 |  | Motor Installation
7.9 |  | Power distribution Control System
7.1 |  | lighting and Small Power Installation
7.11 |  | Heat Tracing Installation
8 |  | Instrument
8.1 |  | Panel Installation
8.2 |  | JB Installation
8.3 |  | Cable Tray Installation
8.4 |  | Cable Installation
8.5 |  | Fiber Optic Cable Installation
8.6 |  | Earthing Installation
9 |  | Telecomm.
9.1 |  | JB Installation
9.2 |  | Cabinet Installation
9.3 |  | Radio Installation
9.4 |  | Antenna Installation
9.5 |  | Tower Installation
9.6 |  | Cable Tray Installation
9.7 |  | Cable Installation
10 |  | Safety
10.1 |  | Foundation/Padding
10.2 |  | Erection
10.3 |  | Grouting